## Tabelle1
Nr. | Task | Start | Planned Completion | Planned Hours | Actual Completion | Actual Hours | Responsible | Status | On Time | Approved By
Planning and Setup
1. | Create screen design | 2025-11-25 | 2025-11-26 | 8 | 2025-11-26 | 8 | Zelenkov | Completed | Yes | Fr. Ley
2. | Create ER/UML diagram of DB | 2025-12-02 | 2025-12-03 | 8 | 2025-12-02 | 6 | Zelenkov |  |  | Fr. Ley
3. | Create class diagram | 2025-12-09 | 2025-12-10 | 6 |  |  | Zelenkov |  |  | Fr. Ley
4. | Create file structure diagram | 2025-12-16 | 2025-12-16 | 4 |  |  | Zelenkov |  |  | Fr. Ley
5. | Setup project, containers & database | 2025-12-17 | 2025-12-23 | 10 |  |  | Zelenkov |  |  | Fr. Ley
Modules and Features
Frontend Part
6. | Module(frontend, UI/UX): User accounts interface with registration/login, order history, wishlist | 2025-12-24 | 2025-12-26 | 8 |  |  | Zelenkov |  |  | Fr. Ley
7. | Module(frontend, UI/UX): Intelligent product search, including autocomplete, typo tolerance, and voice search for easy product discovery | 2025-12-30 | 2025-12-31 | 8 |  |  | Zelenkov |  |  | Fr. Ley
8. | Module(frontend, UI/UX): Product catalog interface with categories and filtering options specific to electronics (brands, specifications, price range) | 2026-01-06 | 2026-01-07 | 8 |  |  | Zelenkov |  |  | Fr. Ley
9. | Module(frontend, UI/UX): Shopping cart interface including add/update/remove products, save for later, and guest checkout | 2026-01-13 | 2026-01-14 | 8 |  |  | Zelenkov |  |  | Fr. Ley
10. | Module(frontend, UI/UX): Fake payment integration supporting credit cards, PayPal, and other local/global gateways. As well as promotions support(promo codes with discounts) given by staff(people who manage products) or admins | 2026-01-20 | 2026-01-21 | 8 |  |  | Zelenkov |  |  | Fr. Ley
11. | Module(frontend, UI/UX): Order management system with tracking, order history, cancellation, and returns processing, an interface to leave reviews | 2026-01-27 | 2026-01-28 | 8 |  |  | Zelenkov |  |  | Fr. Ley
12. | Module(frontend, UI/UX): Contact forms | 2026-02-03 | 2026-02-03 | 4 |  |  | Zelenkov |  |  | Fr. Ley
13. | Module(frontend, UI/UX): Notification pop up | 2026-02-04 | 2026-02-04 | 4 |  |  | Zelenkov |  |  | Fr. Ley
14. | Module(frontend, UI/UX): Inventory management interface with real-time stock level updates, low stock alerts, and easy restocking workflows, promotion codes etc. | 2026-02-10 | 2026-02-11 | 8 |  |  | Zelenkov |  |  | Fr. Ley
15. | Module(frontend, UI/UX): Admin dashboard for managing products, orders, customer data, and promotional campaigns | 2026-02-17 | 2026-02-18 | 8 |  |  | Zelenkov |  |  | Fr. Ley
16. | Module(frontend, UI/UX): Analytics and reporting for sales performance, user behavior, and inventory insights | 2026-02-24 | 2026-02-25 | 8 |  |  | Zelenkov |  |  | Fr. Ley
17. | Module(frontend, UI/UX): Language switcher | 2026-03-03 | 2026-03-03 | 4 |  |  | Zelenkov |  |  | Fr. Ley
Backend Part
18. | Module(backend, communication with DB): User accounts system with registration/login, order history, wishlist | 2026-03-04 | 2026-03-10 | 8 |  |  | Zelenkov |  |  | Fr. Ley
19. | Module(backend, communication with DB): Product catalog system with categories and filtering options specific to electronics (brands, specifications, price range) | 2026-03-11 | 2026-03-17 | 8 |  |  | Zelenkov |  |  | Fr. Ley
20. | Module(backend, communication with DB): Shopping cart functionality including add/update/remove products, save for later, and guest checkout | 2026-03-18 | 2026-03-24 | 8 |  |  | Zelenkov |  |  | Fr. Ley
21. | Module(backend, email sending involved): Fake payment integration supporting credit cards, PayPal, and other local/global gateways. As well as promotions support(promo codes with discounts) given by staff(people who manage products) or admins | 2026-03-25 | 2026-03-31 | 8 |  |  | Zelenkov |  |  | Fr. Ley
22. | Module(backend, communication with DB): Order management system with tracking, order history, cancellation, and returns processing, reviews system | 2026-04-01 | 2026-04-07 | 8 |  |  | Zelenkov |  |  | Fr. Ley
23. | Module(backend): Email sending system | 2026-04-08 | 2026-04-08 | 4 |  |  | Zelenkov |  |  | Fr. Ley
24. | Module(backend, communication with DB): Inventory management interface with real-time stock level updates, low stock alerts, and easy restocking workflows, promotion codes etc. | 2026-04-09 | 2026-04-15 | 8 |  |  | Zelenkov |  |  | Fr. Ley
25. | Module(backend, communication with DB): Admin dashboard for managing products, orders, customer data, and promotional campaigns | 2026-04-16 | 2026-04-22 | 8 |  |  | Zelenkov |  |  | Fr. Ley
26. | Module(backend, communication with DB): Analytics and reporting for sales performance, user behavior, and inventory insights | 2026-04-23 | 2026-04-29 | 8 |  |  | Zelenkov |  |  | Fr. Ley
Text and Content
27. | English translation | 2026-05-05 | 2026-05-05 | 3 |  |  | Zelenkov |  |  | Fr. Ley
28. | German translation | 2026-05-06 | 2026-05-06 | 3 |  |  | Zelenkov |  |  | Fr. Ley
29. | Russian translation | 2026-05-12 | 2026-05-12 | 3 |  |  | Zelenkov |  |  | Fr. Ley
30. | Privacy policy and terms & conditions to protect both the business and customers’ rights. | 2026-05-13 | 2026-05-13 | 3 |  |  | Zelenkov |  |  | Fr. Ley
31. | FAQs | 2026-05-19 | 2026-05-19 | 2 |  |  | Zelenkov |  |  | Fr. Ley
32. | Items' info & descriptions, Users etc. for DB | 2026-05-20 | 2026-05-20 | 4 |  |  | Zelenkov |  |  | Fr. Ley
| Construction | [8 empty] | Fr. Ley
33. | Frontend: Implementation of the main window(s) | 2026-05-26 | 2026-06-02 | 8 |  |  | Zelenkov |  |  | Fr. Ley
34. | Frontend: Logic of the main window(s) | 2026-06-03 | 2026-06-10 | 8 |  |  | Zelenkov |  |  | Fr. Ley
35. | Everything: Implementation of all the modules | 2026-06-16 | 2026-06-23 | 8 |  |  | Zelenkov |  |  | Fr. Ley
36. | Backend: DB Handler best solution implementation | 2026-06-24 | 2026-07-01 | 8 |  |  | Zelenkov |  |  | Fr. Ley
37. | Backend: Data validation and security measures (preventing SQL injection) | 2026-07-07 | 2026-07-14 | 8 |  |  | Zelenkov |  |  | Fr. Ley
Post Development
44. | Test and debugging | 2026-07-15 | 2026-07-22 | 8 |  |  | Zelenkov |  |  | Fr. Ley
45. | Project acceptance and documentation | 2026-07-23 | 2026-07-23 | 4 |  |  | Zelenkov |  |  | Fr. Ley
|  |  | Sum: | 258